## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | As a procurement administrator, I want to add, view, update and delete supplier information so that supplier records can be centrally managed. | MUST HAVE | Database Setup | Backend Team | 3- Completed
S1 | S1 | US-002 | As an employee, I want to register with my name, email, password and role so that I can create an account in the procurement system. | MUST HAVE | No Dependency | Backend Team | 3- Completed
S2 | S2 | US-003 | As a registered user, I want to log in using my email and password so that only authenticated users can access the system. | MUST HAVE | US-002 | Backend Team | 3- Completed
S2 | S2 | US-004 | As a procurement system, I want to validate registration and login details so that invalid data and unauthorized access are prevented. | MUST HAVE | US-002,US-003 | Backend Team | 3- Completed
S2 | S2 | US-005 | As a procurement system, I want to store user and supplier information in a structured database so that the data can be securely persisted and retrieved when required. | MUST HAVE | Database Setup | Backend Team | 3- Completed
S3 | S3 | US-006 | Purchase Order Management – Create, view, update and manage purchase orders from approved purchase requests. | MUST HAVE | Purchase Request + Manager Approval | Backend + Database | 3 – Completed
S3 | S3 | US-007 | Procurement Tracking Dashboard – Track purchase orders, delivery progress and fulfillment status. | MUST HAVE | US-006 | Frontend + Status Workflow | 3 – Completed
S3 | S3 | US-008 | Reporting & Analytics – View total, pending, completed orders and procurement progress through cards, charts and summaries. | MUST HAVE | US-006, US-007 | Frontend + Analytics | 3 – Completed
S3 | S3 | US-009 | Integration Module – Integrate Milestone 3 components with existing system and verify the complete workflow. | MUST HAVE | US-006, US-007, US-008 | Frontend + Backend Integration | 3 – Completed
S4 | S4 | US-010 | As a procurement administrator, I want to view procurement summary cards, track purchase orders, delivery status and procurement progress through a dashboard so that I can monitor the overall procurement process. | MUST HAVE | Module 3 | Frontend + Backend | 3 – Completed
| S4 | US-011 | As a procurement administrator, I want to analyze total, vendor-wise, category-wise and monthly procurement spend using charts and trends so that I can understand spending patterns and improve cost optimization. | MUST HAVE | US-010 | Frontend + Analytics | 3- Completed
S4
S4 | S4 | US-012 | As a procurement administrator, I want to generate filtered procurement reports and export them in PDF and Excel formats so that procurement data can be easily reviewed and shared. | MUST HAVE | US-010, US-011 | Frontend + Backend | 3- Completed
S4 | S4 | US-013 | As a procurement system, I want to complete the remaining workflow improvements, including vendor activation, partial delivery tracking, manager auto-forwarding, undo approval and validation, and perform end-to-end testing so that the complete procurement workflow works correctly. | MUST HAVE | US-010, US-011, US-012 | Full Team | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7